## Thesis Tracker
DAVAO CITY LGU HYBRID RAG ASSISTANT — THESIS PROGRESS SPRINT TRACKER
Linguistically-Engineered Modular RAG Pipeline ¦ Target Submission Deadline: October 23, 2026
| TOTAL TASKS |  |  | TASK COMPLETED |  | PROJECT PROGRESS RATE
| 18 |  |  | 14 |  | 77.78%
MAPPED THESIS SPRINT OPERATIONS
Task ID | Sprint ID | Phase / Chapter | Task Title & Description | Start Date | Due Date | Status | Priority | Deliverable / Output | Mandatory Technical & Data Prerequisites | Fatal Risk
T01 | Sprint 1 | Chapter 3 | Draft Dictionary | 2026-09-04 | 2026-09-10 | Complete | High | Finalize and freeze Layer 1 JSON dictionary (150 terms) mapped strictly across the five eBOSS pillars and dialect false friends | Finalize and freeze Layer 1 JSON dictionary (150 terms) mapped strictly across the five eBOSS pillars and dialect false friends | data/municipal_dictionary_v1.json frozen with 150 entries.
T02 | Sprint 1 | Chapter 3 | Code Dual-Extraction Corpus Engine for City Documents/Citizen Charter | 2026-09-04 | 2026-09-10 | Complete | High | Update splitter to token-based chunking (120 tokens, 20-token overlap) to prevent MiniLM's 128-token sequence truncation | Update splitter to token-based chunking (120 tokens, 20-token overlap) to prevent MiniLM's 128-token sequence truncation | Preprocessing parser outputting clean, token-bounded chunks.
T03 | Sprint 1 | Chapter 3 | Deploy Local LLM via Server (Temp=0, Top-P=0 parameters) | 2026-09-11 | 2026-09-17 | Complete | High | Offline inference pipeline hosted on local hardware | Offline inference pipeline hosted on local hardware | Deterministic query translation endpoint with ambiguity fallback.
T04 | Sprint 1 | Chapter 3 | Draft Expert Rater Coordination Request to Davao Business Bureau | 2026-09-11 | 2026-09-17 | Complete | High | Approved letters securing 3 LGU rater commitments | Approved letters securing 3 LGU rater commitments | Transmitted letters and formal approval for 3 LGU evaluators.
T05 | Sprint 2 | Chapter 3 | Construct 50 Gold-Standard Q&As with Multilingual Query Matrix (150 minimum) | 2026-09-18 | 2026-09-24 | Complete | High | Benchmark expanded to 100 underlying scenario groups (300 query variants: 30 dev groups / 90 queries, 70 held-out test groups / 210 queries). | Benchmark expanded to 100 underlying scenario groups (300 query variants: 30 dev groups / 90 queries, 70 held-out test groups / 210 queries). | Structured benchmark partitioned into 30 dev groups and 70 held-out test groups.
T06 | Sprint 2 | Chapter 3 | Code Automated Evaluation Harness Loop (Hit Rate, MRR, RAGAS) | 2026-09-18 | 2026-09-24 | Complete | High | Python script for batch pipeline evaluation | Python script for batch pipeline evaluation | Batch evaluation pipeline supporting paired test runs.
T07 | Sprint 2 | Chapter 3 | Execute 3 Baseline Architectures & Export Metrics to CSV | 2026-09-18 | 2026-09-24 | Complete | High | Manuscript evaluates 3 frozen configurations: Config A (BM25 Baseline), Config B (Proposed System), and Config C (Ablation: Injection-Disabled). | Manuscript evaluates 3 frozen configurations: Config A (BM25 Baseline), Config B (Proposed System), and Config C (Ablation: Injection-Disabled). | Master automated results CSV comparing baseline, proposed, and ablated pipelines.
T08 | Sprint 3 | Chapter 3 | Generate Randomized Side-by-Side (SxS) Blind Answers for Expert Raters | 2026-09-25 | 2026-10-01 | Complete | High | 40 normalization pairs; 60 answer triples. Fixed 20 groups; adviser amendment 2026-10-26. | 40 normalization pairs; 60 answer triples. Fixed 20 groups; adviser amendment 2026-10-26. | Three two-module packets verified. Post-T07 selection timing disclosed.
T09 | Sprint 3 | Chapter 3 | Build Double-Blind SxS Rater Scoring Interface and Likert Scale Guidelines | 2026-09-25 | 2026-10-01 | Complete | High | M1 fidelity 1-5; M2 relevance and faithfulness 1-4. Separate validated exports. | M1 fidelity 1-5; M2 relevance and faithfulness 1-4. Separate validated exports. | Two-module interface implemented; original Table 2 retained for M2.
T10 | Sprint 3 | Chapter 3 | Execute Blind Relevance Grading Sessions with the 3 LGU Expert Raters | 2026-09-25 | 2026-10-01 | Complete | High | 3 experts: 240 M1 records and 540 M2 records; 1,320 scores validated. | 3 experts: 240 M1 records and 540 M2 records; 1,320 scores validated. | Independent scoring confirmed by researcher. Original provenance correction preserved.
T11 | Sprint 4 | Chapter 4 | Compute Blind Relevance to mathematically verify Rater Agreement | 2026-09-25 | 2026-10-01 | Complete | Medium | Ordinal alpha: fidelity .9354; relevance .9112; faithfulness .8732. Target .80 met. | Ordinal alpha: fidelity .9354; relevance .9112; faithfulness .8732. Target .80 met. | Analysis complete; cluster-bootstrap CIs and provenance limits in T10_T12_REPORT.md.
T12 | Sprint 4 | Chapter 4 | Execute Test to establish Statistical Significance | 2026-09-25 | 2026-10-01 | Complete | Medium | 20 paired scenario groups; seven exact tests with Holm correction. No significant differences. | 20 paired scenario groups; seven exact tests with Holm correction. No significant differences. | Exploratory human comparison complete. No superiority established. See paired_comparisons.csv.
T13 | Sprint 4 | Chapter 4 | Draft Chapter 4 (Results & Discussions) & Code matplotlib/plotly charts | 2026-09-25 | 2026-10-01 | Complete | High | Chapter 4 draft, six tables and three 300-DPI/vector figures prepared 28 October 2026. | outputs/manuscript-closeout-20261028/CHAPTER_4.md; THESIS_RESULTS_REVIEW.pdf | Draft complete, subject to adviser review. Original 177-query retrieval and later 210-query label version reported separately.
T14 | Sprint 5 | Chapter 5 | Draft Chapter 5 (Conclusions, Limitations, & Future Recommendations) | 2026-10-02 | 2026-10-08 | Complete | High | Chapter 5 draft includes objective-based conclusions, limitations and static versioned dictionary recommendations. | outputs/manuscript-closeout-20261028/CHAPTER_5.md | Draft complete. No established system superiority; no unsupported operational benefit claims.
T15 | Sprint 5 | Chapters 1-3 | Revisions Chapter 1-3 | 2026-10-02 | 2026-10-08 | In Progress | High | Source-grounded Chapters 1-3 replacement passages prepared; integration deferred by researcher on 28 October 2026. | outputs/manuscript-closeout-20261028/CHAPTERS_1_TO_3_REVISION_PACKAGE.md | Apply and verify in editable manuscript later. Do not mark full revision complete or repeatedly request deferred files.
T16 | Sprint 6 | Chapters 1-5 | Port Entire Manuscript (Chapters 1 to 5) into Department LaTeX Template | 2026-10-09 | 2026-10-17 | Not Started | High | Chapter 4-5 LaTeX fragments prepared. Official template and full source integration deferred by researcher. | outputs/manuscript-closeout-20261028/latex; review PDF is ReportLab, not a TeX compilation. | Not complete. No official template or TeX compilation; retain pending until researcher resumes integration.
T17 | Sprint 6 | Chapters 1-5 | Conduct Final Adviser Review Round & Implement Emergency Revisions and UREB Submission | 2026-10-09 | 2026-10-17 | Not Started | High | Adviser review brief and decision checklist prepared; no adviser sign-off or UREB submission performed. | outputs/manuscript-closeout-20261028/ADVISER_REVIEW_AND_SUBMISSION.md | Requires actual adviser review, revisions and applicable institutional records.
T18 | Sprint 6 | Chapters 1-5 | Official Submission of Completed Thesis Manuscript to Department Panel | 2026-10-17 | 2026-10-23 | Not Started | High | Submission checklist prepared; no portal upload performed. | outputs/manuscript-closeout-20261028/ADVISER_REVIEW_AND_SUBMISSION.md | Requires final approved manuscript, required attachments and actual submission receipt.
U01 | [5 empty] | Not Started | Medium
U02 | [5 empty] | Not Started | Medium
U03 | [5 empty] | Not Started | Medium
U04 | [5 empty] | Not Started | Medium
U05 | [5 empty] | Not Started | Medium
U06 | [5 empty] | Not Started | Medium
U07 | [5 empty] | Not Started | Medium
U08 | [5 empty] | Not Started | Medium
U09 | [5 empty] | Not Started | Medium
U10 | [5 empty] | Not Started | Medium
U11 | [5 empty] | Not Started | Medium
U12 | [5 empty] | Not Started | Medium
U13 | [5 empty] | Not Started | Medium
U14 | [5 empty] | Not Started | Medium
U15 | [5 empty] | Not Started | Medium

## Sheet1
Task ID | Sprint ID | Phase / Chapter | Task Title & Updated Description | Prerequisites | Start Date | Due Date | Status | Priority | Deliverable / Output
T01 | Sprint 1 | Chapter 3 | Finalize & Freeze Layer 1 Municipal Dictionary: Curate 150 terms across 5 eBOSS pillars and dialect false friends. | Official Citizens' Charters from 5 eBOSS offices; finalized 8-field JSON schema. | 2026-09-04 | 2026-09-10 | In Progress | High | data/municipal_dictionary_v1.json frozen with 150 entries.
T02 | Sprint 1 | Chapter 3 | Code Corpus Ingestion & Token-Based Splitter: Extract eBOSS charter text into 120-token chunks with 20-token overlap. | Document catalog; paraphrase-multilingual-MiniLM-L12-v2 tokenizer; PyMuPDF/TrOCR pipeline. | 2026-09-04 | 2026-09-10 | In Progress | High | Preprocessing parser outputting clean, token-bounded chunks.
T03 | Sprint 1 | Chapter 3 | Deploy Local Mistral 7B Normalization Engine: Configure Ollama inference server with greedy decoding (temp=0, top_p=0) and a 150-token translation limit. | Local GPU runtime (RTX 3060/CUDA); Ollama runtime; constrained few-shot normalization prompt. | 2026-09-11 | 2026-09-17 | Not Started | High | Deterministic query translation endpoint with ambiguity fallback.
T04 | Sprint 1 | Chapter 3 | Transmit LGU Expert Coordination Request: Formal request to Business Bureau (Ms. Maribel T. Paguican) securing 3 trilingual auditors. | Finalized auditor criteria (fluent in English, Tagalog, Bisaya); official institutional communication letter. | 2026-09-11 | 2026-09-17 | Not Started | High | Transmitted letters and formal approval for 3 LGU evaluators.
T05 | Sprint 2 | Chapter 3 | Construct Benchmark Matrix (100 Scenario Groups): Build 300 queries (90 dev, 210 held-out test) with exact charter citations. | T01 dictionary frozen; T02 corpus indexed with exact page references; en bloc scenario-group IDs assigned. | 2026-09-18 | 2026-09-24 | Not Started | High | Structured benchmark partitioned into 30 dev groups and 70 held-out test groups.
T06 | Sprint 2 | Chapter 3 | Code Automated Evaluation Harness Loop: Build batch testing suite for Hit@K and RAGAS Context Precision, Faithfulness, and Answer Relevancy. | T02 BM25 and FAISS indexes built; T03 translation engine operational; RAGAS framework configured. | 2026-09-18 | 2026-09-24 | Not Started | High | Batch evaluation pipeline supporting paired test runs.
T07 | Sprint 2 | Chapter 3 | Execute 3 Frozen Configurations & Grid Search: Tune fusion weights on dev data; evaluate Configs A, B, and C on the 210 test queries. | T05 dev/test split locked; T06 harness ready; BM25/FAISS score min-max normalization implemented. | 2026-09-18 | 2026-09-24 | Not Started | High | Master automated results CSV comparing baseline, proposed, and ablated pipelines.
T08 | Sprint 3 | Chapter 3 | Generate Randomized Double-Blind Audit Corpus: Compile 120 blinded outputs from 20 test groups (60 queries x Configs A & B) with masked system IDs. | T07 held-out inference completed; preselected stratified 20-group subset locked before output inspection. | 2026-09-25 | 2026-10-01 | Not Started | High | 120 randomized, blinded response records with source passages.
T09 | Sprint 3 | Chapter 3 | Build 4-Point Double-Blind Rater Scoring Interface: Create evaluation sheets implementing the approved 4-point ordinal rubric for Relevance and Faithfulness. | T08 output schema finalized; 4-point rubric guidelines codified. | 2026-09-25 | 2026-10-01 | Not Started | High | Auditor scoring platform enforcing the 4-point scale and evidence cross-referencing.
T10 | Sprint 3 | Chapter 3 | Conduct Double-Blind Grading Sessions: Supervise 3 independent LGU domain raters completing 360 reviews (120 items x 3 raters). | T04 auditor appointments confirmed; T08 & T09 audit system deployed; rater calibration completed. | 2026-09-25 | 2026-10-01 | Not Started | High | Completed scoring database of 360 evaluated response records.
T11 | Sprint 4 | Chapter 4 | Compute Krippendorff’s Alpha Inter-Rater Reliability: Calculate ordinal alpha across the 3 independent raters targeting alpha >= 0.80. | T10 evaluation matrix validated with zero missing entries; ordinal difference weighting algorithm configured. | 2026-09-25 | 2026-10-01 | Not Started | Medium | Statistical reliability report confirming rater consensus (alpha >= 0.80).
T12 | Sprint 4 | Chapter 4 | Execute Inferential Statistical Significance Tests: Run Wilcoxon signed-rank and paired tests on automated and human audit metrics. | T07 automated metric CSV; T11 human evaluation ratings. | 2026-09-25 | 2026-10-01 | Not Started | Medium | Statistical significance report demonstrating performance deltas.
T13 | Sprint 4 | Chapter 4 | Draft Chapter 4 (Results & Discussion) & Visualizations: Synthesize empirical answers to RQ1–RQ4 with publication-ready comparative charts. | T07, T11, and T12 data tables finalized; visualization scripts coded. | 2026-09-25 | 2026-10-01 | Not Started | High | Complete Chapter 4 draft with integrated tables and figures.
T14 | Sprint 5 | Chapter 5 | Draft Chapter 5 (Conclusions & Recommendations): Synthesize factual findings, architectural limitations, and e-governance deployment takeaways. | T13 Chapter 4 finalized and approved. | 2026-10-02 | 2026-10-08 | Not Started | High | Complete Chapter 5 draft addressing all research objectives.
T15 | Sprint 5 | Chapters 1–3 | Harmonize Chapters 1 to 3 with Thesis Draft: Align problem statement, objectives, eBOSS scope (removing civil registry/health), and architecture. | Methodology updates locked; obsolete 5-baseline and character-chunking claims purged. | 2026-10-02 | 2026-10-08 | Not Started | High | Revised Chapters 1–3 conforming to the actual experimental execution.
T16 | Sprint 6 | Chapters 1–5 | Port Manuscript into Department LaTeX Template: Compile full text, fix broken labels, verify BibTeX entries. | T13, T14, and T15 written drafts complete; ADDU LaTeX style files loaded. | 2026-10-09 | 2026-10-17 | Not Started | High | Cleanly compiling main.tex and 300-DPI publication PDF.
T17 | Sprint 6 | Chapters 1–5 | Final Adviser Review & Emergency Correction Loop: Address adviser markup, verify equation alignment, and validate citations. | T16 compiled draft submitted for formal sign-off. | 2026-10-09 | 2026-10-17 | Not Started | High | Approved, defense-ready manuscript signed by thesis adviser.
T18 | Sprint 6 | Chapters 1–5 | Official Thesis Manuscript Submission to Panel: Package final PDF and LaTeX source bundle for institutional submission. | T17 formal adviser approval secured; compliance check verified. | 2026-10-17 | 2026-10-23 | Not Started | High | Formal electronic submission confirmation via the ADDU portal.